## Sheet1
Pre-Design Deliverables
June 2017
As part of the deliverables for formal UM review at the end of Pre-Design, the Design Professional shall submit this "Pre-Design Deliverables" document to the University's Design Manager. On the "Pre-Design Deliverables" document, the Design Professional shall indicate the status of each required item (a check mark is interpreted to mean that an item has been included in the deliverables). On or attached to the "Pre-Design Deliverables" document, the Design Professional shall identify all items NOT included in the review package. Note Design Professional shall not contact City of Ann Arbor. Design Manager is the conduit for all communication between Design Professional and user groups, Campus Planning, City of Ann Arbor etc.
Item |  | Task | Required Yes / No | Date Received | Responsibility | Comment
Real Estate and Regulatory Review | 1 | Topographic survey required. Obtain Minimum Boundary/ Topographic Survey Requirements |  |  | Design Manager | Provide Link to actual topo survey requirements
| 2 | Identify anticipated impacts to adjacent private property (anticipated grading, staging, vegetation removal or trimming, access needs, utility work) to Campus Planning Prior to proceeding with a design that requires impacts. |  |  | Design Manager with Design Professional | Design Manager shall review impacts with Campus Planning early in Pre-design.
| 3 | Verify title search has been requested to ensure there are no encumbrances that will impact site development. |  |  | Real Estate Office requested by DM | Note topographical survey form indicates title search is surveyors requirement to obtain.
| 4 | Are any impacts to the City Right of Way anticipated (any new or modified drive way cuts, utility installations or connections et al, tree removals?) See City of Ann Arbor Preliminary plan review Check list |  |  | Design Manager shall provide City of Ann Arbor checklist | Link to City of Ann Arbor preliminary plan review checklist (on sharepoint)
| 5 | Related to above, will a temporary or permanent ROW Occupancy Agreement be required? |  |  | Design Manager with Design Professional
| 6 | Are any temporary or permanent easements required? |  |  | Design Manager with Design Professional
| 7 | Has a code review been conducted to ensure compliance with applicable regulation for interior and exterior spaces? |  |  | Design Professional | Understanding items like fire access limitations, egress issues etc. can more effectively ensure the project is properly programmed and the initial budget does not underestimate these items.
| 8 | Will new or renovated facility be Bureau Fire Services Compliant? |  |  | DM to clarify with user group
| 9 | Identify any historically significant features that shall be protected and/ or restored |  |  | Design Manager with Design Professional
UM Master Plan Review | 1 | Site Planning Principles to help guide the conceptual planning approach have been requested and received. |  |  | DM coordinate with Campus Planning (CP) | Site Planning Principles shall be incorporated into Basis of Design (BOD)
| 2 | Has the Project Team reviewed applicable State, City , UM traffic and transportation plans? |  |  | DM coordinate with CP
| 3 | Has the Project Team met with CP to review the UM Master Plan to ensure compliance? |  |  | DM to coordinate with CP
Environmental Review | 1 | Have sustainable goals been established for the project - including opportunities for Stormwater Best Management Practices? |  |  | DM coordinate with CP and AEC Sustainability Coordinator - site SD item 3
| 2 | Are there any regulated water bodies of the State, wetland, drains and streams within the site boundary? |  |  | DM to review with EH&S
| 3 | Is site greater than an acre or within 500' of water of the State? A soil erosion and sedimentation control plan may be required. |  |  | DM to review with EH&S
| 4 | Has Project Team considered a post-construction storm water management plan if size of is greater or equal to an acre? |  |  | Design Professional | link to storm water management procedure if earth disturbance is greater than an acre
| 5 | Has a Floristic Quality Assessment been requested? |  |  | Design Professional
| 6 | Has a Threatened and Endangered Species report been requested? |  |  | Design Professional
| 7 | Has a Phase 1 Environmental Assessment been prepared? |  |  | DM to review with EH&S
| 8 | Has the Project Team consulted existing data or requested a soils survey to determine the presence of contaminated soils or hazardous material? |  |  | DM to review with EH&S
| 9 | Has the Project Team obtained a Tree Survey and Evaluation? Significant trees as identified in the Tree Evaluation shall be protected per the UM Tree Preservation Policy in design through to construction completion. |  |  | DM to contact Grounds Services
Site | 1 | Has consideration been given to how the proposed building setbacks, drives, walks and parking relate to adjacent campus development (the campus neighborhood)? |  |  | DM to coordinate with CP
| 2 | Does the site contain existing memorial trees, donor benches, plaques, sculpture, class gifts or the like? If proposing new furniture, specify U-M preferred site furnishings. |  |  | DM to coordinate with CP | Early notice is key to planning for preservation, relocation etc.
| 3 | Will public art be a component of the design of the site and building? |  |  | DM to coordinate with CP | Schematic Design Phase
| 4 | Develop a conceptual level lighting plan, consider light spill to neighbors. For context sensitive lighting consider a photometric analysis. |  |  | Design Professional
| 5 | Establish site lighting goals, what areas to be illuminated, footcandle targeted goals, types of site lighting fixtures. Pedestrian, Parking etc. |  |  | Design Professional
| 6 | If Non-Capital Planning project, has project received CEOC/EEDR review & support? |  |  | DM to coordinate with CP
| 7 | Identify impacts from building/site generated noise, exhaust, shading, window reflections, site lighting, etc. on surrounding properties, and preliminary mitigation measures assumed, e.g. berms, sound attenuation. |  |  | Design Professional
Circulation, Transit, Parking and Building Services | 1 | Will any existing U-M parking or loading spaces be impacted by the project? Verify any potential Downtown Development Authority (DDA) metered parking impacts. |  |  | DM to coordinate with CP | Note: At roughly $75k per removed DDA metered space, this should be considered in the conceptual phase when project goals are being identified and updated as the project evolves.
| 2 | If parking is to be removed, has the Project Team provided a sound rationale and/ or plan for replacement parking? |  |  | DM to coordinate with CP
| 3 | Has a traffic survey (including pedestrian counts) been performed to ensure proposed improvements do not negatively impact existing pedestrian, vehicular, transit and parking system? |  |  | DM to coordinate with CP
| 4 | Coordinate with Building Services for waste management planning |  |  | DM | Site item 1j in SD
| 5 | Loading dock location evaluated including size and weight of trucks making deliveries |  |  | Design Professional
| 6 | Has an adequate amount of strategically located bike parking been provided? |  |  | Design Professional | Evaluate if additional bike parking will be needed. Pre-planning location to be integral to site design is important.
| 7 | Will the project impact existing transit stops or propose new? |  |  | Design Professional | site selection and building entry location may be influenced by transit access
| 8 | Will project impact ADA egress? |  |  | Design Professional | Accessibility is good design and not an after thought
| 9 | Are any emergency access impacts anticipated? |  |  | DM to coordinate with EH&S - Fire Safety
| 10 | Consider service vehicle parking need |  |  | Design Professional
| 11 | Verify Fire Hydrant Coverage. |  |  | Design Professional
Utilities & Infrastructure (U-M and Local) | 1 | Has a Systems Narrative been developed to ensure plan compliance and to ensure the existing utility systems (storm, electrical, ITCOM, gas, sanitary, domestic water, fire water, chilled water and steam) can support the proposed project requirements? |  |  | DM to Coordinate with City and CP | Document in Basis of Design
| 2 | Will the proposed development impact the existing water service configuration? |  |  | DM to Coordinate with City and CP | Link to City of Ann Arbor preliminary plan review checklist (on sharepoint)
| 3 | Has the Facilities Conditions Assessment (FCA) data base been reviewed by Project Team to determine if there are any deficient items to be picked up and funded within project scope? |  |  | DM to Coordinate
Programming | 1 | Develop program for building occupancy, including overall square footage, MBC occupancy classification etc. |  |  | Design Professional
| 2 | review Provost space use guidelines |  |  | Design Professional
| 3 | Provide square footage estimates of each major space type, e.g. wet lab, dry lab, vivarium, office. |  |  | Design Professional
| 4 | DG 2.1 Owner Project Requirements (OPR) - Outline Owner's Project Requirement and Basis of Design document providing all the information required in this checklist. |  |  | Design Professional | OPR and BOD shall be fully developed during the design phases.
| 5 | Note if building is a 'High Rise' |  |  | Design Professional
Building Interior and Exterior | 1 | Describe special occupancy environmental requirements: temperature, humidity, vibration control, acoustical separation, etc. List the specific requirements as best know at this stage. |  |  | Design Professional
| 2 | Define occupancy types |  |  | Design Professional
| 3 | Is this a renovation project over $10M construction cost? If so perform pre-construction infrared thermal imaging to detect areas of excess air leakage. |  |  | DM
| 4 | Describe how the requirements of U-M DG 3.2 will be attained, in particular to achieve energy goals above code. |  |  | Design Professional
| 5 | Identify proposed location of major M & E equipment, e.g. penthouse |  |  | Design Professional
| 6 | Provide overview of envelope construction, e.g. curtain wall, mass, frame. Percentage using glass |  |  | Design Professional
| 7 | Describe envelope enhancements to reduce energy, e.g. additional insulation, overhangs, electro chromatic glass, trombe walls. |  |  | Design Professional
| 8 | For existing buildings, describe the approach planned to improve the envelope's energy performance. |  |  | Design Professional
| 9 | For existing bldg.'s, description of how project will accommodate ASHRAE 90.1 energy code requirements for alterations. |  |  | Design Professional
Elevators | 1 | Determine type of elevator |  |  | Design Professional
| 2 | Backup power source identified, if required |  |  | Design Professional
| 3 | Note if any of the elevators will be an accessible means of egress |  |  | Design Professional
HVAC | 1 | Identify potential system types, multiple options are acceptable |  |  | Design Professional
| 2 | Identify utilities source: chilled water, gas, steam, etc. |  |  | Design Professional
| 3 | Identify special HVAC, hydronic, and exhaust systems: process air handlers, process CHW, smoke evacuation systems, laboratory exhaust, etc. |  |  | Design Professional
| 4 | Identify major special MEP redundancy requirements, e.g. redundant vivarium AHUs on emergency power with dedicated chiller. |  |  | Design Professional
Plumbing | 1 | Identify potential systems types, multiple options are acceptable |  |  | Design Professional
& Piping | 2 | Identify utilities source: domestic water, fire protection water, storm, sanitary |  |  | Design Professional
| 3 | Identify special plumbing and process systems: RO/DI, lab gases, acid waste, etc. |  |  | Design Professional
Fire Protection (Mechanical) - continued | 1 | fire suppression - required? |  |  | Design Professional
Fire Protection (Mechanical) | 2 | fire suppression - source |  |  | Design Professional
| 3 | Identify special fire protection systems |  |  | Design Professional
| 4 | Is fire pump required? |  |  | Design Professional
Lighting | 1 | Lighting concepts identified for interior and exterior systems |  |  | Design Professional
| 2 | Identify target footcandle levels for common space types |  |  | Design Professional
| 3 | Identify common lighting control strategies |  |  | Design Professional
Electrical Power Distribution | 1 | Conceptually, identify the approximate service size and from where will it be served (i.e.. campus loop, DTE, other?) Identify ductbank location in relationship to building |  |  | Design Professional
| 2 | Substation location, in building or adjacent? Accessibility? Does the building need single-ended, double-ended, or multiple substations? |  |  | Design Professional
| 3 | Note any high voltage or specialty power requirements |  |  | Design Professional
| 4 | Does the facility require a lightening protection system? |  |  | Design Professional
| 5 | Note emergency and standby power requirements. Emergency generator, is it needed? If needed consider location and fuel source |  |  | Design Professional
| 6 | Allocated Space for electrical closets |  |  | Design Professional
| 7 | Identify what types of loads are emergency and which ones are optional/ standby. Conceptually identify the approximate generator size. |  |  | Design Professional
Fire Alarm and Emergency Communications | 1 | Determine if a fire alarm system is required. |  |  | Design Professional
| 2 | Note if MOSCAD system will perform the functions as a Central Station Monitoring facility. |  |  | Design Professional
| 3 | Identify building entrance selected for emergency response. Note fire alarm panel location. |  |  | Design Professional
| 4 | Indicate if fire alarm system will be used as a mass notification system. |  |  | Design Professional
| 5 | Note if project scope will include an Emergency Radio Responder Coverage System? |  |  | Design Professional
| 6 | Identify if toxic/flammable gas or other special alarm systems are anticipated |  |  | Design Professional
Communications (Including voice, data & video systems) | 1 | Identify Tele/Data service entrance point into building. BE room location and location of communication duct bank in relationship to the building. |  |  | Design Professional
| 2 | Are any assistive listening systems required? |  |  | Design Professional
| 3 | Identify audio/ visual system requirements. |  |  | Design Professional
| 4 | Allocate space for IT closets |  |  | Design Professional
| 5 | Note if ERRC system components will be installed in IT closets |  |  | Design Professional
| 6 | Note if project scope will include a cell phone signal reinforcement system |  |  | Design Professional
Security (including CCTV and Card Access Control Systems) | 1 | Identify security system needs (security cameras, card access, etc.) |  |  | Design Professional
| 2 | Note is project scope includes CCTV |  |  | Design Professional
LEED and Sustainability | 1 | Will project pursue formal LEED Certification? |  |  | Design Professional
| 2 | Create a "simple box" energy model to identify and document energy and water reduction strategies, to include different building orientations. Provide estimated annual energy, Energy Use Index, and energy cost for the building. For buildings with atriums, break out energy, EUI, and energy cost for the atrium portion. Complete the LEED Integrative Process Worksheet to explain baseline assumptions used in the energy model and describe potential load reduction strategies. Provide preliminary peak diversified cooling and heating loads identified by the model. |  |  | Design Professional
|  | List of project sustainability goals, including LEED, energy conservation measures, and storm water management. |  |  | DM coordinate with CP and AEC Sustainability Coordinator
| 3 | Complete the LEED Site Assessment Worksheet to explain relationships between site features and how the features influenced the project. |  |  | Design Professional
Cost and Design Timeline | 1 | provide estimated cost of construction |  |  | Design Professional
| 2 | provide design timeline/estimated design phase durations |  |  | Design Professional
Notes